## Sheet1
Project: Puzzle Gauntlet |  |  | Weekly Sprint Sheet |  | Team Members | Team Members | Email
As of May 1st |  |  |  |  | Eugenio Perez | Eugenio Perez | eperez77@uic.edu
[5 empty] | Kaveesha Weerasiri | Kaveesha Weerasiri | kweera2@uic.edu
[5 empty] | Charly Sandoval | Charly Sandoval | csando66@uic.edu
[5 empty] | Adrian Zavala | Adrian Zavala | azaval9@uic.edu
Action Item | Item ID | Team Member | Last Week | This week | Next week | Next Week | Issues | Date
Write codebase for JavaFX from modified RPSLS code | 1 | Eugenio | - | Modified RPSLS code from Proj3/4 so that it has the GUI, and Server/Client functionality. Pushed to github |  | Make improvements to base code wherever needed
Research Timer | 2 | Eugenio | Researched methods to implement timer to make the game more competitive/stop users from solving puzzles
Timer Server Communication | 3 | Charly | - | Implement a timer on the server side that will determine the total time players have to complete a puzzle
Timer | 4 | Kaveesha | - | - |  | Once someone wins or the timer is reached, the user is prompted a pop up window that asks the user whether they want to quit or play again
Design and implement a puzzle | 5 | Eugenio | Come up with a Puzzle to implement in JavaFX, Decided on Sudoku | Implement code for Sudoku in my assigned scene. Make it so it's not the same sudoku puzzle every time you open the door
Design and implement a puzzle | 6 | Kaveesha | Come up with a Puzzle to implement in JavaFX | Design a puzzle around morse code translation, design a puzzle converting binary to hex, and design a puzzle based off math. |  | -
Design and implement a puzzle | 7 | Adrian | Come up with a Puzzle to implement in JavaFX | Design a couple puzzles based on pictures, to guess the song
Design and implement a puzzle | 8 | Charly | Come up with a Puzzle to implement in JavaFX | Figure out Client/Server on node.js |  | Design puzzles based displaying video characters and have client guess the video game
Adrian's puzzle music snippets | 9 | Adrian | - | Research for a standard library possiblity/implment a button to play a snippet of the song that has to be guessed |  | -
Drop down menu for puzzles | 10 | Adrian | - | Created a menu for Adrian's branch |  | When all puzzles are finished, incorporated a drop down menu for the player to select the puzzle they want to do
Write Design Doc | 11 | All | Created doc on google docs so that we can all refer to it, and make changes as needed |  |  | Update the design document as more of the UI is implemented
See if node.js is a preferable way to do htis project | 12 | All | Research node.js, by looking at professors code and other node examples on the internet | Decide that Node is not the preferred way to go about this project |  | -
Implement a game over pop up | 13 | Kaveesha/Charly | Have the game display a pop up when the timer reaches 0, that will force the client to quit or play again | Implement a game over pop up |  | -
Server/Client Integration: Scoring and gameplay | 14 | Eugenio | Reimplement Updating scoreboard, only make game playable when 4 players are connected