## Sheet1
Project: Puzzle Gauntlet |  |  | Weekly Sprint Sheet |  | Team Members | Team Members | Email
Week of: 4/14/2019 |  |  |  |  | Eugenio Perez | Eugenio Perez | eperez77@uic.edu
[5 empty] | Kaveesha Weerasiri | Kaveesha Weerasiri | kweera2@uic.edu
[5 empty] | Charly Sandoval | Charly Sandoval | csando66@uic.edu
[5 empty] | Adrian Zavala | Adrian Zavala | azaval9@uic.edu
Action Item | Item ID | Team Member | Last Week | This week | Next week | Next Week | Issues | Date
Decide Game to make | 1 | All | Decide game to make |  |  | Hopefully stay with the idea of a puzzle gauntlet
Write codebase for JavaFX from modified RPSLS code | 2 | Eugenio | - | Upload to Github |  | Make improvements
node js base code | 3 | Adrian | - | Server/Client |  | Try to make a code base for a client/server in node js
| 4 | Adrian | - | - |  | Implement a timer on each puzzle, so the clients only have 60-90 seconds to answer
puzzles | 5 | Eugenio | Design a Puzzle | Work on a Sudoku puzzle |  | Puzzles based on riddles, logic puzzles involving buttons
puzzles | 6 | Kaveesha | Design a Puzzle | Same as the Item ID's for 11 and 12 |  | Design a puzzle around morse code translation, design a puzzle converting binary to hex, and design a puzzle based off math. Try to make Adrian/Eugenio's code to work in Node.js before Saturday/try to do my own version, if not work on puzzle in javaFX
puzzles | 7 | Adrian | Design a Puzzle |  |  | Design a couple puzzles based on songs lyrics, to guess the song
puzzles | 8 | Charly | Design a Puzzle | Figure out Client/Server on node.js |  | Design puzzles based displaying video characters and have client guess the video game
| 9 | All | Design Doc |  |  | Update the design document as more of the UI is implemented
| 10 | All | GUI beautification/Design For individual Puzzles |  |  | Work on individual puzzle and try to make it look nice
See if node.js is a preferable way to do htis project | 11 | All | Research node.js | Becomes node.js masters |  | Be able to dream in node.js
Decide on how to write project | 12 | All | Decide by Saturday whether to use Node or JavaFX | Looked at Professor's code, as well as other node.js examples. Will use the code Base of whoever is farthest along in their implementation by Friday |  | Will use the code Base of whoever is farthest along in their implementation by Friday, should we decide to use Node